## Summary
Summary
Build Stage | Estimated Cost | Total Cost Paid to Date | Costs Due | Variance To Estimate | Float Balance
Demoliton Enabling works | 0 | 26689.32 | 8205.2 | -34894.52
Goundworks | 0 | 7907.17 | 217.17 | -8124.34
Masonry | 0 | 579.52 | 0 | -579.52
Roofing | 0 | 0 | 0 | 0
Electrical | 0 | 0 | 0 | 0
Plumbing & Heating | 0 | 424.75 | 0 | -424.75
Joinery | 0 | 5061.52 | 4687.79 | -9749.31
Windows and doors | 0 | 120 | 0 | -120
Drylining & Plaster/Render | 0 | 0 | 0 | 0
Decoration | 0 | 0 | 0 | 0
Landscaping | 0 | 0 | 0 | 0
Finishes Schedule | 0 | 0 | 0 | 0
Steelwork | 0 | 360 | 0 | -360
Flooring/Tiling | 0 | 27.65 | 27.65 | -55.3
Kitchen | 0 | 0 | 0 | 0
Extra | 0 | 0 | 0 | 0
Project Management Fee | 0 | 0 | 0 | 0
Total | 0 | 41169.93 | 13137.81 | -54307.74 | 133526.57

## Cost Tracker
Beeholme Cost Tracker
Build Stage | Date | Invoice Reference | Description | Amount Paid | Costs Paid Direct By Customer | Refunds | Costs Due | Total Build Stage Cost to Date |  | Build Stage | Description | Estimate | Actual Cost to Date | Variance to Estimate
Professional Fees |  |  |  | 12077.29 | 0 | 0 | 15950 | 28027.29 |  | Demo/Enabling |  | 0 | 28027.29 | -28027.29
| 2025-05-23 | 751 | Ardent Consulting | 2789.29 | [5 empty] | Variance to Estimate
| 2025-05-23 | INV-0578 | Weddles | 5112
| 2024-12-13 | Inv108 | Nordbarn Ltd | 3000 |  |  | 3450
| 2025-01-21 | Inv109 | Nordbarn Ltd |  |  |  | 12500
| 2025-09-03 | 137678 | London Building Control | 1176
Demoliton Enabling works |  |  |  | 18484.12 | 0 | 0 | 8205.2 | 26689.32 |  | Demo/Enabling |  | 0 | 26689.32 | -26689.32
| 2025-03-01 | 36378 | Bradwell Skips | 252 | [5 empty] | Variance to Estimate
| 2025-03-02 | A20931126456 | Plumbfix - Saw Blades | 98.48
| 2025-04-15 | INV-8688 | Mapmatic - Survey | 3900
| 2025-04-30 | BOXIB2280 | BOXI - PPE | 47.15
| 2025-04-30 | BOXIB2281 | BOXI - PPE | 10.87
| 2025-05-01 | 37414 | Bradwell Skips | 264
| 2025-05-01 | BOXIB2282 | BOXI - Shovel and Brush | 53.99
| 2025-05-08 | BOXIB2285 | BOXI - Claw Hammer | 34.78
| 2025-05-10 | Milestone55 | Site Management - Sam Hatch | 2000
| 2025-05-12 | 37551 | Bradwell Skips | 264
| 2025-05-21 | INV5295 | Marsh Tree Care | 1200
| 2025-05-21 | 135523 | Tiger Supplies | 62.34
| 2025-05-27 | 37799 | Bradwell Skips | 264
| 2025-05-29 | 4176 | Haywood Engineering | 360
| 2025-06-04 | N/A | Sainsbury's - Petrol | 13.49
| 2025-06-05 | 11516 | Marsh Design | 1020
| 2025-06-05 | BOXIB2293 | BOXI - Spray ,pads, chisel bits | 182.36
| 2025-06-06 | BOXIB2295 | BOXI - Bolts, twisted nails, sand cement | 49.06
| 2025-06-12 | BOXIB2294 | BOXI - Strongboys | 175.25
| 2025-05-31 | Milestone56 | Site Management - Sam Hatch 15.5 days May | 3100
| 2025-06-18 | Milestone57 | Site Management - Sam Hatch 12 days Jun17th | 2400
| 2025-06-17 | 38118 | Bradwell Skips | 264
| 2025-06-19 | 276 | D&A Muck Away | 420
| 2025-06-23 | N/A | Asda - Fuel | 8.79
| 2025-06-24 | N/A | Asda - Fuel | 16.58
| 2025-06-24 | 277 | D&A Muck Away | 420
| 2025-06-27 | BOXIB2308 | BOXI - Chisel Bits | 49.8
| 2025-06-30 | BOXIB2299 | BOXI - Digger, Dumper, Pecker | 979.2
| 2025-07-07 | INV-2844 | Get Loos - Toilet (Delivery & Collection Charge) | 124.8
| 2025-07-10 | BOXIB2322 | BOXI - PPE, 20mm SDS | 22.9
| 2025-07-08 | BOXIB2314 | BOXI - Mesh, chairs, castles , wire |  |  |  | 1847.02
| 2025-07-15 | BOXIB2332 | BOXI - SDS Bits |  |  |  | 49.8
| 2025-07-16 | N/A | Morrisons - Batteries | 2.5
| 2025-07-16 | BOXIB2337 | BOXI - tools |  |  |  | 136.37
| 2025-07-18 | 38585 | Bradwell Skips | 264
| 2025-07-07 | INV-2949 | Get Loos - Portable Toilet Hire (until July 22) |  |  |  | 129.6
| 2025-07-24 | N/A | ASDA - Petrol | 6
| 2025-07-24 | N/A | ASDA - Diesel | 5.97
| 2025-07-25 | BOXIB2348 | BOXI - Sthill Saw |  |  |  | 73.2
| 2025-07-28 | MIL30 | Tradefix - Hangers and Screws | 67.82
| 2025-07-28 | BOXIB2350 | BOXI - Bitumen, saw, tape, roller |  |  |  | 129.73
| 2025-07-31 | BOXIB2358 | BOXI - Drill bit, damp proof tape. |  |  |  | 78.06
| 2025-08-05 | BOXIB2361 | BOXI - D4 Glue, Screws |  |  |  | 217.66
| 2025-08-19 |  | BOXI - Nails | 79.99
| 2025-08-20 | BOXIB2376 | BOXI - Nails and egger |  |  |  | 119.76
| 2025-08-26 | 39152 | Bradwell Skips |  |  |  | 264
| 2025-10-04 | SI-1036 | Headway Scaffold |  |  |  | 5160
Goundworks |  |  |  | 7690 | 0 | 0 | 217.17 | 7907.17 |  | Groundworks |  | 0 | 7907.17 | -7907.17
| 2025-06-11 | 102 | Joe Naylor | 60 | [5 empty] | Variance to Estimate
| 2025-06-26 | 101 | Evie Brett | 90
| 2025-07-15 | 104 | Joe Naylor | 120
| 2025-07-15 | 105 | Joe Naylor | 120
| 2025-07-28 | MIL**** | Sam Hatch - Site Management until 25/07/25 | 5600
| 2025-07-16 | 00207 | Timbrell - Raft | 1100
| 2025-07-16 | BOXIB2333 | BOXI - Concrete Float |  |  |  | 57.17
| 2025-07-25 | 106 | Joe Naylor | 180
| 2025-08-01 | 107 | Joe Naylor | 180
| 2025-08-22 | 108 | Joe Naylor | 120
| 2025-08-29 | 109 | Joe Naylor | 60
| 2025-08-29 | 110 | Joe Naylor | 60
| 2025-08-29 | 111 | Joe Naylor |  |  |  | 80
| 2025-08-29 | 112 | Joe Naylor |  |  |  | 80
Masonry |  |  |  | 579.52 | 0 | 0 | 0 | 579.52 |  |  |  | 0 | 579.52 | -579.52
| 2025-06-10 | BOXIB2297 | BOXI - 6/2 | 73.18 | [5 empty] | Variance to Estimate
| 2025-07-08 | BOXIB2328 | BOXI - Blocks sand cement | 494.16
| 2025-07-31 | A2252428442 | Screwfix | 12.18
Roofing |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Electrical |  |  |  | 364.02 | 0 | 0 | 0 | 364.02 |  |  |  | 0 | 364.02 | -364.02
| 2025-05-16 | INV-10534 | IPS Electrical | 329.03 | [5 empty] | Variance to Estimate
| 2025-07-31 | A22523105609 | Screwfix - Socket Set | 34.99
Plumbing & Heating |  |  |  | 424.75 | 0 | 0 | 0 | 424.75 |  |  |  | 0 | 424.75 | -424.75
| 2025-05-29 | INV-2022 | K.Hall Plumbing | 192.32 | [5 empty] | Variance to Estimate
| 2025-06-25 | BOXIB2304 | BOXI - Drainage | 232.43
Joinery |  |  |  | 373.73 | 0 | 0 | 4687.79 | 5061.52 |  |  |  | 0 | 5061.52 | -5061.52
| 2025-07-15 | BOXIB2327 | BOXI - 6x Lintels |  |  |  | 184.32 |  |  | Variance to Estimate
| 2025-07-05 | 125626 | Wardmans | 193.2
| 2025-07-19 | 125857 | Wardmans | 153.6
| 2025-07-19 | 639316 | Salisbury & Wood | 26.93
| 2025-07-19 | 225146 | Charles Gregory - need to confirm amount
| 2025-08-04 | BOXIB2352 | BOXI - Timber |  |  |  | 3685.26
| 2025-08-04 | BOXIB2359 | BOXI - Timber |  |  |  | 818.21
Windows and doors |  |  |  | 120 | 0 | 0 | 0 | 120 |  |  |  | 0 | 120 | -120
| 2025-09-04 | N/A | ATM - Cash Matlock Glass | 120 | [5 empty] | Variance to Estimate
Drylining & Plaster/Render |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Decoration |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Landscaping |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Finishes Schedule |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Steelwork |  |  |  | 360 | 0 | 0 | 0 | 360 |  |  |  | 0 | 360 | -360
| 2025-08-15 | INV4176 | Haywood Engineering | 360 | [5 empty] | Variance to Estimate
Flooring/Tiling |  |  |  | 0 | 0 | 0 | 27.65 | 27.65 |  |  |  | 0 | 27.65 | -27.65
| 2025-07-16 | BOXIB2334 | BOXI - Skater Tiles |  |  |  | 27.65 |  |  | Variance to Estimate
Kitchen |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Extra |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
Variance to Estimate
Project Management Fee |  |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  | Project Management Fee Part 1 Of 5 | [6 empty] | Variance to Estimate
Project Management Fee Part 2 Of 5
Project Management Fee Part 3 Of 5
Project Management Fee Part 4 Of 5
Project Management Fee Part 5 Of 5
Total (Not Including Project Management Fee) |  |  |  | 40473.43 | 0 | 0 | 29087.81 | 69561.24 |  |  | 0 | 0 | 41533.95 | -41533.95
Total (Including Project Management Fee) |  |  |  | 40473.43 | 0 | 0 | 29087.81 | 69561.24 | 0 |  | 0 | 0 | 41533.95 | -41533.95
Note on C125: Lynn Gunning ¦ Milestone Builders: Was BB2291 or MIL34

## Float
Float Tracker
Date Paid | Invoice No | Amount Paid
2024-11-11 | BEE01 | 174000
Total Float Paid |  | 174000
Amount Paid |  | 40473.43
Costs Paid Direct |  | 0
Refunds |  | 0
Float Balance |  | 133526.57
Float Balance After Costs Due |  | 104438.76

## Cash Tracker (hidden)
Woodfoot Road Cost Tracker
Build Stage | Date | Invoice Reference | Description | Amount Paid | Costs Paid Direct By Customer | Refunds | Costs Due | Total Build Stage Cost to Date
Demoliton Enabling works |  |  |  | 3772.2 | 0 | 0 | 0 | 3772.2
| 2021-09-23 | WOO004 | Travis Perkins - Mini Digger | 500
| 2021-09-28 | WOO005 | OCD Plumbing | 4.34
| 2021-10-05 | WOO005 | Quadrant Building Control | 300
| 2021-09-30 | WOO005 | Euroloo | 204
| 2021-10-13 | WOO005 | Quadrant Building Control | 594
| 2021-10-01 | AWAIT REF | Euroloo | 56.58
| 2021-11-18 | AWAIT REF | Yorkshire Water | 332
| 2021-11-01 | AWAIT REF | Euroloo | 141.42
| 2021-12-01 | AWAIT REF | Euroloo | 108.43
| 2022-01-18 | AWAIT REF | Rapid Skips | 215
| 2021-01-20 | AWAIT REF | Waste Removal Charge - Milestone Builders | 215 | Lynn Aware
| 2022-01-19 | AWAIT REF | Wickes (Dave Platts Paid For This Order) | 12
| 2022-01-22 | AWAIT REF | Hireforce | 102.72
| 2022-01-21 | AWAIT REF | Pagets | 635.22
| 2022-01-21 | AWAIT REF | Pagets | 6.49
| 2022-01-21 | AWAIT REF | Sam Lombard | 345
Goundworks |  |  |  | 4028.64 | 0 | 0 | 0 | 4028.64
Quote List | 2021-10-01 | WOO005 | Kieran Atkinson | 1200
| 2021-10-01 | WOO005 | Jack Thomas | 270
| 2021-11-04 | AWAIT REF | Jack Thomas | 90
| 2021-11-02 | AWAIT REF | Pagets | 1647.53
| 2021-11-02 | AWAIT REF | Pagets | 365.11
| 2021-11-03 | AWAIT REF | Jack Thomas | 90
| 2021-10-19 | AWAIT REF | Rotherham Mini Digger | 276
| 2021-11-10 | AWAIT REF | Jack Thomas | 90
Masonry |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Roofing |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Electrical |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Plumbing & Heating |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Joinery |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Windows and doors |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Drylining & Plastering/Rendering |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Decoration |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Landscaping |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Finishes Schedule |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Steelwork |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Flooring/Tiling |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Kitchen |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Extra |  |  |  | 0 | 0 | 0 | 0 | 0
Quote List
Project Management Fee |  |  |  | 25000 | 0 | 0 | 5000 | 30000
Quote List | 2021-03-19 | WOO001 | Project Management Fee - 50% | 15000
| 2021-09-23 | WOO002 | Project Management Fee Part 1 Of 2 | 10000
|  |  | Project Management Fee Part 2 Of 2 |  |  |  | 5000
Total (Not Including Project Management Fee) |  |  |  | 7800.84 | 0 | 0 | 0 | 7800.84
Total (Including Project Management Fee) |  |  |  | 32800.84 | 0 | 0 | 5000 | 37800.84